## Overview
Total amount of (non basic) tests: | 147
Complete tests: | 105
Partial tests (missing asset): | 36
Components not tested | 0
Missing tests: | 6

## BadgeClass CRUD (hidden)
| 31 | Onderwijsinstelling |  |  | Badge class |  |  | Te valideren actie |  |  |  |  | status/verwachte effort
Testfile naam |  | MBO | HBO | UNI | Regular | Micro | Extra | Aanmaken | Muteren | verwijderen | Publiceren | Copy | POC | Small effort | Medium effort | Large effort
BadgeCreation | x | x |  |  | x |  |  | x |  |  |  |  | x
EditBadge | x | x |  |  | x |  |  |  | x | [5 empty] | x
RemoveBadge | x | x |  |  | x |  |  |  |  | x |  |  |  | x
badgeCreation | x | x |  |  |  | x |  | x |  |  |  |  | x
EditBadge | x | x |  |  |  | x |  |  | x | [5 empty] | x
RemoveBadge | x | x |  |  |  | x |  |  |  | x |  |  |  | x
badgeCreation | x | x |  |  |  |  | x | x |  |  |  |  | x
EditBadge | x | x |  |  |  |  | x |  | x | [5 empty] | x
RemoveBadge | x | x |  |  |  |  | x |  |  | x |  |  |  | x
badgeCreation | x |  | x |  | x |  |  | x |  |  |  |  | x
EditBadge | x |  | x |  | x |  |  |  | x | [5 empty] | x
RemoveBadge | x |  | x |  | x |  |  |  |  | x |  |  |  | x
badgeCreation | x |  | x |  |  | x |  | x |  |  |  |  | x
EditBadge | x |  | x |  |  | x |  |  | x | [5 empty] | x
RemoveBadge | x |  | x |  |  | x |  |  |  | x |  |  |  | x
badgeCreation | x |  | x |  |  |  | x | x |  |  |  |  | x
EditBadge | x |  | x |  |  |  | x |  | x | [5 empty] | x
RemoveBadge | x |  | x |  |  |  | x |  |  | x |  |  |  | x
badgeCreation | x |  |  | x | x |  |  | x |  |  |  |  | x
EditBadge | x |  |  | x | x |  |  |  | x | [5 empty] | x
RemoveBadge | x |  |  | x | x |  |  |  |  | x |  |  |  |  | x
CopyRegularBadge | x |  |  | x | x | [6 empty] | x |  | x
badgeCreation | x |  |  | x |  | x |  | x |  |  |  |  | x
EditBadge | x |  |  | x |  | x |  |  | x | [5 empty] | x
CopyMicroBadge | x |  |  | x |  | x | [5 empty] | x |  |  | x
RemoveBadge | x |  |  | x |  | x |  |  |  | x |  |  |  | x
badgeCreation | x |  |  | x |  |  | x | x |  |  |  |  | x
EditBadge | x |  |  | x |  |  | x |  | x | [5 empty] | x
CopyExtraBadge | x |  |  | x |  |  | x |  |  |  |  | x |  |  | x
RemoveBadge | x |  |  | x |  |  | x |  |  | x |  |  |  | x
x

## Badge Aanvragen (hidden)
|  | Type badge |  |  | Toekennen |  |  |  |  | status/verwachte effort
Testfile naam | 12 | Regular | Micro | Extra | Direct EPPN | Direct mail | Bulk | Aanvraag backpack | Aanvraag API student administratie systeem | POC | Small effort | Medium effort | Large effort | Out of scope
AwardBadge | x | x |  |  | x |  |  |  |  | x
AwardBadge | x | x |  |  |  | x |  |  |  |  | x
AwardBadge | x | x | [5 empty] | x |  | x
Out of scope | x | x | [6 empty] | x |  |  |  |  | x
AwardBadge | x |  | x |  | x | [5 empty] | x
| x |  | x |  |  | x |  |  |  |  | x
AwardBadge | x |  | x |  |  |  |  | x |  |  | x
Out of scope | x |  | x | [5 empty] | x |  |  |  |  | x
AwardBadge | x |  |  | x | x | [5 empty] | x
| x |  |  | x |  | x |  |  |  |  | x
AwardBadge | x |  |  | x |  |  |  | x |  |  | x
Out of scope | x |  |  | x |  |  |  |  | x |  |  |  |  | x

## Badge acties (hidden)
| Generieke badges acties (enkele test case) |  | status/verwachte effort
Testfile naam | Actie | 12 | POC | Small effort | Medium effort | Large effort | Out of scope
Actie student
Proof of concept | Badge claimen | x | x |  |  |  |  | Actie teacher
Student → ReceiveBadge | Badge niet accepteren | x |  |  | x |  |  | Actie institution admin
Proof of concept | Badge publiek maken | x | x |  |  |  |  | Actie system admin
Student → EditBadge | Badge delen | x |  |  |  | x
BLOCK → always invalid | Badge valideren - valide | x |  | x
| Badge valideren - invalide | x |  |  | x
BadgeclassAdmin → Revoke badge | Badge intrekken - MBO | x |  |  |  | x
BadgeclassAdmin → Revoke badge | Badge intrekken - HBO | x |  |  | x
Student → BadgeRemoval | Badge intrekken - Uni | x |  |  | x
StudentInteraction → awardBadge | Aangevraagde badge toekennen | x | x
InstitutionAdmin → EntityControl → Issuergroup → Delete | Issuer groep verwijderen | x |  |  | x
Out of scope | Instituut verwijderen | x |  |  |  |  | x
student19@university-example.org

## Gebruikers rollen (hidden)
Progress |  | Rechten betreffende |  |  |  |  | Valideren dat deze actie wel of niet mag |  |  |  | status/verwachte effort
| 17 | Instelling | Issuer | Badges | Backpack | Koppeling student administratie systeem | Inzien | Aanmaken | Muteren | Verwijderen | POC | Small effort | Medium effort | Large effort | Out of scope | Actie student
Actie teacher
Out of scope | x | x |  |  |  |  | x | [7 empty] | x | Actie institution admin
Out of scope | x | x | [5 empty] | x | [6 empty] | x | Actie system admin
Out of scope | x | x | [6 empty] | x | [5 empty] | x
Out of scope | x | x | [7 empty] | x |  |  |  |  | x
UserManagement → Issuers → Read | x |  | x |  |  |  | x | [5 empty] | x
UserManagement → Issuers → Create | x |  | x |  |  |  |  | x |  |  |  |  | x
UserManagement → Issuers → Update | x |  | x | [5 empty] | x |  |  |  | x
UserManagement → Issuers → Delete | x |  | x | [6 empty] | x |  |  | x
Teacher → BadgeInteraction → BadgeCreation | x |  |  | x |  |  | x | [5 empty] | x
Teacher → BadgeInteraction → BadgeCreation | x |  |  | x |  |  |  | x |  |  |  |  | x
Teacher → BadgeInteraction → BadgeEdit | x |  |  | x |  |  |  |  | x |  |  |  | x
Teacher → BadgeInteraction → BadgeRemoval | x |  |  | x | [5 empty] | x |  |  | x
Backpackpage → Login | x |  |  |  | x |  | x | [5 empty] | x
Out of scope | x |  |  |  |  | x | x | [7 empty] | x
Out of scope | x |  |  |  |  | x |  | x | [6 empty] | x
Out of scope | x |  |  |  |  | x |  |  | x
Out of scope | x |  |  |  |  | x |  |  |  | x |  |  |  |  | x

## Entiteiten beheer (hidden)
Progress |  | Entiteit |  |  |  | Actie |  |  | status/verwachte effort
| 10 | Instelling | Issuer group | Issuer | staff user | Muteren | Aanmaken | Verwijderen | POC | Small effort | Medium effort | Large effort | Out of scope | Actie student
Actie teacher
Out of scope | x | x |  |  |  | x | [6 empty] | x | Actie institution admin
InstitutionAdmin → EntityControl → Issuergroup → Create | x |  | x |  |  | x |  |  |  |  | x |  |  | Actie system admin
InstitutionAdmin → EntityControl → Issuergroup → Edit | x |  | x |  |  |  | x |  |  |  | x
InstitutionAdmin → EntityControl → Issuergroup → Delete | x |  | x |  |  |  |  | x |  |  | x
UserManagement → Issuers → Update | x |  |  | x |  | x |  |  |  |  | x
UserManagement → Issuers → Create | x |  |  | x |  |  | x |  |  |  | x
UserManagement → Issuers → Delete | x |  |  | x |  |  |  | x |  |  | x
${role} → Invite | x |  |  |  | x | x | [5 empty] | x
EntityControl → UserManagement → WOUser | x |  |  |  | x |  | x |  |  |  |  | x
EntityControl → UserManagement → WOUser | x |  |  |  | x |  |  | x |  |  |  | x

## Test distribution (hidden)
ROLE
| Create | Invite | Institution admin | Issuergroup admin | Issuer admin | Badgeclass admin
|  | Institution admin | Succeed | Fail |  |  | Succeed | Test possibility
| Issuergroup |  | Succeed | Fail |  |  | Fail | Test impossibility
SUBJECT |  | Issuergroup admin |  | Succeed | Fail
| Issuer |  |  | Succeed | Fail
|  | Issuer admin |  |  | Succeed | Fail
| Badgeclass |  |  |  | Succeed | Fail
|  | Badgeclass admin |  |  |  | Succeed

## Badgeclass interaction
|  |  |  | Badgeclass admin | Issuer admin
|  | WO | Create | BadgeclassInteraction → Create | Badgeclassinteraction → Create
Tested | Path to test | HBO |  | BadgeclassInteraction → Create | Badgeclassinteraction → Create
Test missing asset | Path to test | MBO |  | BadgeclassInteraction → Create | Badgeclassinteraction → Create
Test impossibility | Path to test | WO | Read | BadgeclassInteraction → Read | BadgeclassInteraction → Read
Not tested (yet) | X | HBO |  | BadgeclassInteraction → Read | BadgeclassInteraction → Read
Not to be tested |  | MBO |  | BadgeclassInteraction → Read | BadgeclassInteraction → Read
|  | WO | Update |  | BadgeclassInteraction → Update
|  | HBO |  |  | BadgeclassInteraction → Update
|  | MBO |  |  | BadgeclassInteraction → Update
|  | WO | Copy |  | BadgeclassInteraction → Copy
|  | HBO |  |  | BadgeclassInteraction → Copy
|  | MBO |  |  | BadgeclassInteraction → Copy
|  | WO | Delete |  | BadgeclassInteraction → Delete
|  | HBO |  |  | BadgeclassInteraction → Delete
|  | MBO |  |  | BadgeclassInteraction → Delete

## Issuer interaction
|  |  |  | Issuer admin | Issuergroup admin
|  | WO | Create | IssuerInteraction → Create | IssuerInteraction → Create
Tested | Path to test | HBO |  | IssuerInteraction → Create | IssuerInteraction → Create
Test missing asset | Path to test | MBO |  | IssuerInteraction → Create | IssuerInteraction → Create
Test impossibility | Path to test | WO | Read | IssuerInteraction → Read | IssuerInteraction → Read
Not tested (yet) | X | HBO |  | IssuerInteraction → Read | IssuerInteraction → Read
Not to be tested |  | MBO |  | IssuerInteraction → Read | IssuerInteraction → Read
|  | WO | Update |  | IssuerInteraction → Update
|  | HBO |  |  | IssuerInteraction → Update
|  | MBO |  |  | IssuerInteraction → Update
|  | WO | Delete |  | IssuerInteraction → Delete
|  | HBO |  |  | IssuerInteraction → Delete
|  | MBO |  |  | IssuerInteraction → Delete

## Issuergroup interaction
|  |  |  | Issuergroup admin | Institution admin
|  | WO | Create | IssuergroupInteraction → Create | IssuergroupInteraction → Create
Tested | Path to test | HBO |  | IssuergroupInteraction → Create | IssuergroupInteraction → Create
Test missing asset | Path to test | MBO |  | IssuergroupInteraction → Create | IssuergroupInteraction → Create
Test impossibility | Path to test | WO | Read | IssuergroupInteraction → Read | IssuergroupInteraction → Read
Not tested (yet) | X | HBO |  | IssuergroupInteraction → Read | IssuergroupInteraction → Read
Not to be tested |  | MBO |  | IssuergroupInteraction → Read | IssuergroupInteraction → Read
|  | WO | Update |  | IssuergroupInteraction → Update
|  | HBO |  |  | IssuergroupInteraction → Update
|  | MBO |  |  | IssuergroupInteraction → Update
|  | WO | Delete |  | IssuergroupInteraction → Delete
|  | HBO |  |  | IssuergroupInteraction → Delete
|  | MBO |  |  | IssuergroupInteraction → Delete

## Student interaction
|  |  |  | WO | HBO | MBO
|  | Student based | Request regular badge | BasicsCatalogStudent | BasicsCatalogStudent | BasicsCatalogStudent
Tested | Path to test |  | Request extra curricular badge | X | X | X
Test missing asset | Path to test |  | Request micro credential | X | X | X
Test impossibility | Path to test |  | Receive badge | Backpack → RequestedBadge | Backpack → RequestedBadge | Backpack → RequestedBadge
Not tested (yet) | X |  | Direct receive badge | Backpack → ReceivedBadge | Backpack → ReceivedBadge | Backpack → ReceivedBadge
Not to be tested |  |  | Reject direct badge | Backpack → ReceivedBadge | Backpack → ReceivedBadge | Backpack → ReceivedBadge
|  |  | Accept direct badge | Backpack → ReceivedBadge | Backpack → ReceivedBadge | Backpack → ReceivedBadge
|  |  | Reject accepted badge | Backpack → EditBadge | Backpack → EditBadge | Backpack → EditBadge
|  |  | Make badge public | Backpack → ShareBadge | Backpack → ShareBadge | Backpack → ShareBadge
|  |  | Share badge | Backpack → ShareBadge | Backpack → ShareBadge | Backpack → ShareBadge
|  |  | Validate badge | Backpack → ShareBadge | Backpack → ShareBadge | Backpack → ShareBadge
|  |  | Have badge revoked | Backpack → ReceivedBadge | Backpack → ReceivedBadge | Backpack → ReceivedBadge
|  |  | Have badge denied | Backpack → RequestedBadge | Backpack → RequestedBadge | Backpack → RequestedBadge
|  | Teacher based | Deny request with reason | StudentInteraction → DenyBadge | StudentInteraction → DenyBadge | StudentInteraction → DenyBadge
|  |  | Deny request without reason | StudentInteraction → DenyBadge | StudentInteraction → DenyBadge | StudentInteraction → DenyBadge
|  |  | Revoke awarded badge | StudentInteraction → RevokeBadge | StudentInteraction → RevokeBadge | StudentInteraction → RevokeBadge
|  |  | Award requested badge | StudentInteraction → AwardBadge | StudentInteraction → AwardBadge | StudentInteraction → AwardBadge
|  |  | Direct award badge using EPPN | StudentInteraction → AwardBadge | StudentInteraction → AwardBadge | StudentInteraction → AwardBadge
|  |  | Direct award using mail | StudentInteraction → AwardBadge | StudentInteraction → AwardBadge | StudentInteraction → AwardBadge

## Admin rights
Folder/Inviter
|  |  |  | Badgeclass admin | Issuer admin | Issuergroup admin | Institution admin
Tested | Path to test | WO | Invite badgeclass admin | Invite → Badgeclass admin
Test missing asset | Path to test |  | Edit badgeclass admin | Invite → Badgeclass admin
Test impossibility | Path to test | MBO | Invite badgeclass admin | Invite → Badgeclass admin
Not tested (yet) |  |  | Edit badgeclass admin | Invite → Badgeclass admin
Not to be tested |  | HBO | Invite badgeclass admin | Invite → Badgeclass admin
|  |  | Edit badgeclass admin | Invite → Badgeclass admin
|  | WO | Invite issuer admin | Invite → IssuerAdmin | Invite → IssuerAdmin
|  |  | Edit issuer admin |  | Invite → IssuerAdmin
|  | MBO | Invite issuer admin | Invite → IssuerAdmin | Invite → IssuerAdmin
|  |  | Edit issuer admin |  | Invite → IssuerAdmin
|  | HBO | Invite issuer admin | Invite → IssuerAdmin | Invite → IssuerAdmin
|  |  | Edit issuer admin |  | Invite → IssuerAdmin
|  | WO | Invite issuergroup admin |  | Invite → IssuergroupAdmin | Invite → IssuergroupAdmin
|  |  | Edit issuergroup admin |  |  | Invite → IssuergroupAdmin
|  | HBO | Invite issuergroup admin |  | Invite → IssuergroupAdmin | Invite → IssuergroupAdmin
|  |  | Edit issuergroup admin |  |  | Invite → IssuergroupAdmin
|  | MBO | Invite issuergroup admin |  | Invite → IssuergroupAdmin | Invite → IssuergroupAdmin
|  |  | Edit issuergroup admin |  |  | Invite → IssuergroupAdmin
|  | WO | Invite institution admin |  |  | Invite → InstitutionAdmin | Invite → InstitutionAdmin
|  |  | Edit institution admin |  |  |  | Invite → InstitutionAdmin
|  | MBO | Invite institution admin |  |  | Invite → InstitutionAdmin | Invite → InstitutionAdmin
|  |  | Edit institution admin |  |  |  | Invite → InstitutionAdmin
|  | HBO | Invite institution admin |  |  | Invite → InstitutionAdmin | Invite → InstitutionAdmin
|  |  | Edit institution admin |  |  |  | Invite → InstitutionAdmin

## Institution interaction
|  |  |  | Institution admin | System admin
|  | WO | Create
Tested | Path to test | HBO
Test missing asset | Path to test | MBO
Test impossibility | Path to test | WO | Read
Not tested (yet) | X | HBO
Out of scope |  | MBO
|  | WO | Update
HBO
MBO
|  | WO | Delete
HBO
MBO

## Badge distribution
Badgename | Badgetype | Receive/request/reward usage in testcase | NOTES:
Law and Politics | Regular | Receive by Student → Backpack → ReceiveBadge | Used by Institution admin to invite badgeclassadmin
Circulation and Breathing | Regular | Reward by Student → Backpack → EditBadge
Introduction to Psychology | Regular | Reward by Student → Backpack → ReceiveBadge | Used to login by Student → Logout
Cognitive Psychology | Regular | Denied by Badgeadmin → DenyBadge
Psychometrics | Regular | Reward by Teacher → StudentInteraction → AwardBadge
Group Dynamics | Regular | Request by Student → BasicsCatalog | Used by anonymous to look at
Introduction to Political Science | Regular | Rewarded by Student → Backpack → ShareBadge
History of Political Thought | Regular | Rewarded by Student → Backpack → ShareBadge
Research Methods | Regular | Read by Student → BasicsCatalog
Growth and Development | Regular | Rewarded by BadgeAdmin → AwardBadge | Read by BadgeAdmin → SeeBadge. Used by badgeclass admin to invite badgeclass admin
Regulation and Integration | Regular | Denied by Badgeadmin → DenyBadge
Digestion and Defense | Regular | Denied by Badgeadmin → DenyBadge
|  | Tests without dedicated badge: | Amount:
|  | Student → Requestedbadge | 2
|  | StudentInteraction → RevokeBadge | 1
|  | Student → Backpack → Receivedbadge | 1